Cooper University’s George Bradshaw Library Document Delamination Project

PROBLEM

Cooper University’s George Bradshaw Library holds valuable historical documents from the United States’ founding, including a draft of the United States Constitution, which are deteriorating because they were laminated. After ten years laminate on documents disintegrates and reacts with the encapsulated document and destroys it. This has caused a fourfold issue. First, the vinegar smell from the deteriorating laminate is now a public safety hazard for both viewers and our archive librarians, as it can cause health problems. Second, the documents are being destroyed the longer they stay laminated. Third, viewership has declined by members of the University by 30%. Fourth, viewership from the public has declined by 50%, which has led to a net loss to the University’s arts fund by 2 million dollars in the last year.

SOLUTION

The library is proposing a full-scale delamination project. This will require the documents to be treated by an outsourced delamination company. Outsourcing this project is deemed best by our staff, as the library does not have the resources to effectively delaminate the documents safely. The process for delamination requires putting a document into a chemical bath. If the documents are not delaminated correctly, it can cause the following issues. First, staff could be injured. Second, the text could be completely removed from the document. Third, the text could become severely faded. Therefore, we deem outsourcing this project to a delaminator to be the best course of action.

REQUIRED RESOURCES

Staffing: Library staff will change shelving location on all items, put items in crates, load them on book carts, load them in a van, and take them to the library’s van accompanied by a library security guard to the delamination center.

Equipment: Crates, library book carts, respirators, chemical resistant gloves, and a van.

Training: Two staff members will attend a series of trainings online with the National Archives on delamination. Additionally, they will meet with other librarians online who have done similar projects. The training will be two business days, which would equal sixteen hours. This training will be to learn about safely transporting the documents in a healthy and secure way from the archives to the delaminator.

PROJECT PARTNERS

Library Access Services Department

Library Archive Department

Library Cataloging Department

Library Security Department

The University’s Advancement Team

The University History Department

The project will be led by the library’s Archive Department. They will facilitate communication between the University project partners, bring the documents to the delaminator, communicate monthly to the University, our project partners, and donors, and coordinate the documents return. Specifically, the library’s Archive Department will work with the Cataloging Department to change the shelving locations upon the removal and return of the historic documents. Additionally, initially, they will work with Access Services Department to order the PPE (respirators and chemical resistant gloves) and supplies (crates) to safely transfer the items to the delaminator. Finally, the Archives Department will ensure that the documents are safely handled by always being accompanied by Library Security when depositing and returning the documents.

Our project partners will be informed of the progress of the project each month. A contact member from the Library Archive Department will be designated to facilitate all communication between the Dean of the Library, the Dean of Academic Affairs, the library departments, our project partners, and donors.

ASSESSMENT

Success will be measured by the 100% delamination of all documents. Additionally, since delamination can pose a risk to the documents, albeit not as great as the damage over time by not delaminating them, the return of the documents with their structural integrity intact, as well as legibility that is at least at 90%, will be factored into our measurement of a successful project outcome.

A project report will be submitted to the Dean of Academic Affairs by the Head of our Archive Department by May 2, 2024, which will reflect the progress of the project and the number of documents that have been fully and successfully delaminated. Also, there will be note if any documents were too far deteriorated to be delaminated, and whether those that have been delaminated have maintained a 90% of the integrity and legibility of the former document.

BUDGET

| Salaries | Expenses | Comments |
| --- | --- | --- |
| Project Manager .5 FTE | $37,500 | $36.06 hr., 1,040 hours |
| Archival Assistant .25 FTE | 9,500 | 18.27 hr., 520 hours |
| Access Services Librarian 0.0005 FTE | 18 | 18.27 hr., 1 hour |
| Cataloging Librarian .2 FTE | 12,000 | 28.85 hr., 416 hours |
| Library Security .1 FTE | 3,500 | 16.83 hr., 208 hours |
| Advancement Team Member 0.0024 FTE | 192 | 38.46 hr., 5 hours |
| History Department Adjunct Professor 0.0024 FTE | 144 | 28.85 hr., 5 hours |
| Benefits |  |  |
| Project Manager .5 FTE | 11,250 | 30% benefits |
| Archival Assistant .25 FTE | 2,850 | 30% benefits |
| Access Services Librarian 0.0005 FTE | 5 | 30% benefits |
| Cataloging Librarian .2 FTE | 3,600 | 30% benefits |
| Library Security .1 FTE | 1,050 | 30% benefits |
| Advancement Team Member 0.0024 FTE | 58 | 30% benefits |
| History Department Adjunct Professor 0.0024 FTE | 43 | 30% benefits |
| Contractual Services |  |  |
| High Quote for Outsourced Delamination Company | 60,000 | For 2,000 documents |
| Medium Quote for Outsourced Delamination Company (Quote used in the Total) | 20,000 | For 2,000 documents |
| Low Quote for Outsourced Delamination Company | 15,000 | For 2,000 documents |
| Library Materials |  |  |
| Book Carts | 1,000 | 2 carts |
| Supplies |  |  |
| Chemical Resistant Gloves | 67 | 5 pack |
| Crates | 725 | 48 pack |
| Respirators | 100 | 4 pack |
| Respirator Cartridges | 48 | 4 pack |
| Travel |  |  |
| Gas | 240 | 3.00 price per gallon for 8 gallons of gas for once a month for 10 months |
| Equipment |  |  |
| None |  |  |
| Total | $103,938 | Total calculation using medium quote for outsourced services |

TIMELINE

| Due date | Activity |
| --- | --- |
| December 4, 2023 | Dean of the Library approves project proposal & budget |
| December 11, 2023 | Dean of the Library secures Dean of Academic Affairs support for the project & budget |
| December 18, 2023 | Dean of Academic Affairs secures Provost’s support for project |
| January 22, 2024 | Discuss the upcoming project logistics with library staff & ask for input |
| January 22, 2024 | Announce the official start of the project to the University, project partners, and donors. |
| February 5, 2024 | The project head and all involved with handling the documents will attend a webinar with the National Archives on the secure handling of disintegrating laminated documents. |
| February 6, 2024 | Zoom call #1 with archival staff with a library who has successfully gone through the delamination process |
| February 7, 2024 | Zoom call #2 with archival staff with a library who has successfully gone through the delamination process |
| February 8, 2024 | Have Access Services order any needed materials for the project |
| February 20, 2024 | Develop project timeline and submit to Dean of the Library who will submit to the Dean of Academic Affairs |
| March 4, 2024 | Identify and meet with project contact in both the Advancement Department and confirm our contact from the History Department. |
| March 11–15, 2024 | Box historical documents in crates and send list at end of the week to the Cataloging Librarian to change shelving location |
| March 18–22, 2024 | Box historical documents in crates and send list at end of the week to the Cataloging Librarian to change shelving location |
| March 25–28, 2024 | Box historical documents in crates and send list at end of the week to the Cataloging Librarian to change shelving location |
| April 2, 2024 | Two librarians from the Archive Department and a member of Library Security will transport the documents from the archives, load the van, and take them to the delaminator |
| April 3, 2024 | First payment of 40% sent to delaminator from Archive’s Department |
| May 1, 2024 | The Archive Department and Library Security will pick up the first box of 200 delaminated documents |
| May 2, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and the University arts donors will hear of the project through mass email |
| May 3, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| May 6–10, 2024 | All items will be unpacked and reshelved |
| June 3, 2024 | The Archive Department and Library Security will pick up the second box of 200 delaminated documents |
| June 4, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| June 5, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| June 10–14, 2024 | All items will be unpacked and reshelved |
| July 1, 2024 | The Archive Department and Library Security will pick up the third box of 200 delaminated documents |
| July 2, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| July 3, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| July 8–12, 2024 | All items will be unpacked and reshelved |
| August 1, 2024 | The Archive Department and Library Security will pick up the fourth box of 200 delaminated documents |
| August 2, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| August 5, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| August 5–8, 2024 | All items will be unpacked and reshelved |
| August 9, 2024 | The library team will meet with project partners for a mid-project Zoom call review. |
| September 3, 2024 | The Archive Department and Library Security will pick up the fifth box of 200 delaminated documents |
| September 4, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| September 5, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| September 9–13, 2024 | All items will be unpacked and reshelved |
| October 1, 2024 | The Archive Department and Library Security will pick up the sixth box of 200 delaminated documents |
| October 2, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| October 4, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| October 7–11, 2024 | All items will be unpacked and reshelved |
| November 4, 2024 | The Archive Department and Library Security will pick up the seventh box of 200 delaminated documents |
| November 6, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| November 7, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| November 12–15, 2024 | All items will be unpacked and reshelved |
| December 2, 2024 | The Archive Department and Library Security will pick up the eighth box of 200 delaminated documents |
| December 3, 2024 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| December 4, 2024 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| December 9–13, 2024 | All items will be unpacked and reshelved |
| January 6, 2025 | The Archive Department and Library Security will pick up the ninth box of 200 delaminated documents |
| January 7, 2025 | A progress report will be emailed to all library staff, the Dean of Academic Affairs, our project partners, and donors |
| January 8, 2025 | A list of all returned items will be sent to the Cataloging librarian to change the shelving location |
| January 13–17, 2025 | All items will be unpacked and reshelved |
| February 3, 2025 | The Archive Department and Library Security will pick up the tenth box of 200 delaminated documents |
| February 4, 2025 | A progress report will be emailed to all library staff, the Dean of Academic Affairs and our project partners |
| February 5, 2025 | Archives Department sends final payment to the delaminator |
| February 5, 2025 | A list of all returned items will be sent to the Cataloging Librarian to change the shelving location |
| February 10–14, 2025 | All items will be unpacked and reshelved |
| February 18–20, 2025 | Review inventory list with Cataloging Librarian to ensure all documents were returned |
| February 24, 2025 | Write a report about the success of the project for the library staff, the Dean of Academic Affairs, and our project partners |
| February 25, 2025 | Send email out to our University’s arts donors about the success of the project |
| February 26, 2025 | The Access Services Librarian will put an official article on the library website about the project’s completion and the library Archive’s Department will send a University wide email about the completion of the project. |